Project Report

Title: Customer Churn Prediction using R

1. Introduction

Customer churn is a major challenge for subscription-based businesses. This project aims to analyze customer data from a telecom company and build predictive models to identify customers at risk of leaving. By leveraging R’s statistical and machine learning capabilities, the project provides actionable insights to reduce churn and improve retention.

2. Project Objective

- Goal: Develop a churn prediction model in R.

- Problem Statement: Identify drivers of churn and predict which customers are likely to leave.

- Expected Outcome:

  - A validated predictive model.

  - Insights into customer behavior.

  - Recommendations for churn reduction strategies.

3. Research Background

- Rationale: Reducing churn directly increases profitability.

- Literature Review:

  - Logistic regression and decision trees are common churn prediction methods.

  - Key features include tenure, billing issues, and service usage.

  - Ensemble methods (Random Forest, XGBoost) often outperform single models.

4. Methodology & Project Phases

| Phase | Description | Tools in R | Duration |
| --- | --- | --- | --- |
| Data Collection | Gather telecom churn dataset (CSV/SQL/API). | readr, DBI | 1 week |
| Data Cleaning | Handle missing values, outliers, encode categorical variables. | dplyr, tidyr, caret | 2 weeks |
| Exploratory Data Analysis | Visualize churn patterns, correlations, distributions. | ggplot2, corrplot | 2 weeks |
| Model Development | Train Logistic Regression, Random Forest, XGBoost. | caret, randomForest, xgboost | 3 weeks |
| Model Evaluation | Compare models using accuracy, precision, recall, F1, ROC-AUC. | caret, pROC | 1 week |
| Reporting & Deployment | Create final report, dashboards, recommendations. | RMarkdown, Shiny | 2 weeks |

Total Duration: ~11 weeks

5. Roles & Responsibilities

- Project Manager: Define scope, track progress, manage risks.

- Data Analyst: Perform EDA, visualize churn trends.

- Data Engineer: Collect and preprocess data.

- ML Engineer: Build and evaluate models.

- Report Writer: Document findings and prepare final report.

(If working solo, all roles are assumed sequentially.)

6. Risk Management

| Risk | Mitigation |
| --- | --- |
| Poor Data Quality | Robust cleaning, imputation, validate sources. |
| Class Imbalance | Apply resampling (SMOTE, undersampling). |
| Overfitting Models | Use cross-validation, regularization, ensembles. |
| Time Overruns | Stick to timeline, prioritize deliverables. |
| Limited Domain Knowledge | Consult experts, review literature. |

7. Resource Allocation

- Software: RStudio, R packages (caret, ggplot2, randomForest, xgboost, shiny).

- Hardware: Laptop/PC with ≥8GB RAM.

- Data: Telecom churn dataset (Kaggle or company-provided).

- Documentation: RMarkdown for reproducible reports, GitHub for version control.

8. Expected Deliverables

- Cleaned dataset.

- EDA visualizations.

- Predictive models with evaluation metrics.

- Final report (Word/PDF/RMarkdown).

- Interactive dashboard (optional, via Shiny).

9. Conclusion

This project provides a structured roadmap for churn prediction using R. By following the outlined phases, the project ensures reproducibility, actionable insights, and practical recommendations for reducing customer attrition.